Pawnee District

Eagle Scout Packet

Prepared for Troop 74.

Current as of December 29, 2005

Pawnee District Eagle Scout Packet

Step 1: Choose Your Project	3

Project Suggestions:	3

Step 2:  Initial Planning and Project Write-up	4

Project Description	4

Who Will Benefit and How Will They Benefit	4

Planning Details	4

Present Condition	4

Plans/Drawings/Designs	5

Materials	5

Tools	5

Supplies	5

Schedule (Plan of Work)	5

Step-by-Step Instructions	5

Financial Plan (Budget)	6

Written /Printed Information	6

Helpers/Workers	6

Adult Supervision	6

Work Site	6

Transportation	6

Safety	7

Step 3:  Initial Project Approval	7

Step 4:  Completing the Project	7

Step 5:  Final Write-up	7

Step 6:  Final Project Approvals	8

Reference:  Recommendations	8

Pawnee District Eagle Scout Packet

This guide has been developed to help the Scouts understand expectations; aid them in preparing their plan, and to serve as a benchmark for the adults to judge a project plan.

The most difficult part of your Eagle Service Leadership Project is getting started.  The Eagle Project will require a lot of time to complete, possibly 2 to 6 months.  Because it is not necessary to complete all 21 Eagle merit badges before beginning your project, you should chose a period when you can most afford to put in the time.  For example, summer might be a better time than the period just before Christmas.  Remember, you must work with other scouts and leaders and their busy schedules, not just your own.  For the leaders and your own sake, please begin your project at least 6 months before your 18th birthday.  All Eagle requirements must be completed, and that includes the project and the final write-up, before you are 18 (NO exceptions).  Plan ahead!  However, you must plan and execute your project while a Life Scout. It is never too early to start.

Your Eagle Project must demonstrate leadership and provide service to a worthy institution other that the Boy Scouts of America.  Leadership must be a major part of the project.  You must be totally in charge of the project.  Adults should be used only: 1) as resources (for example: provide ideas for projects, technical knowledge or serve as advisers), or 2) performing tasks youth are unable to do (for example: providing transportation, providing two deep leadership, or operating dangerous equipment).  For the optimum development of your leadership skills, adults (especially your parents or guardians) should be involved as little as possible.  Your parents should not serve as project advisers.  To complete your project you may recruit members of your own or other troops, non-Scouts, or adults, if you choose.

See the first page of the Eagle Service Project Workbook for all requirements.  You should look for a project idea, which is original, truly valuable, and a challenge to you.  Project ideas can be found in many places:  in the newspaper, at your church, at your school, or from community organizations.  Get the word out that you are looking for project ideas and see what input you receive.  As you look around for ideas, write down several that interest you.  You should not spend much time planning a project until you have talked the idea over with your Scoutmaster or other troop adviser to ensure that you have a good project idea.

# Step 1: Choose Your Project

## Project Suggestions:

You may choose to build something, do service for someone, present a program to a group, or correct a problem area for the benefit of an authorized organization.

Some projects completed by Pawnee District Eagles are listed below:

| Repaired furniture and windows for a church. Built nesting boxes for waterfowl. Built a footbridge on the Konza Prairie. Repaired and refinished antique school desks for historical society. Prepared a walking tour of an historic area in Manhattan. Built 3 newspaper-recycling boxes for an elementary school. Built 2 camp chuck boxes for a Girl Scout Troop. Collected 450 pair of used eyeglasses for the Lions Club program for the needy. Repaired fencing at a church sponsored nursing home and organized a social function for the residents. Repaired a church sign and re-landscaped around it. | Built a janitor closet in a church Fellowship Hall. Conducted a book fair for a church run bookstore. Collected children’s books and toys and setup a play area at a public hospital neighborhood clinic. Painted a mural on the wall of his Synagogue depicting Jewish life. Conducted a program for kindergarten children about dangers of abduction and fingerprinted them for parents. Modified church's storage building, adding double door for tractor access, shelves, permanent window covering. Planted trees and placed boulders in a local park to stop off-road vehicles from damaging grounds. Built bat cages at a Church Built benches on an elementary school playground Built picnic tables at Manhattan High School Landscaped memorial gardens at a Church cemetery |
| --- | --- |

You can find more suggestions for projects at this internet address: http://www.scoutorama.com/eagle.html

# Step 2:  Initial Planning and Project Write-up

After you have talked over possible project ideas with your troop leaders (Eagle Scout Coordinator, Mr. Jon R. Anderson; 1117 Jakob’s Court, Manhattan, KS, 785-776-7764) and chosen the right one for you, it is time to begin the detail planning and initial write-up which will be submitted to the District Eagle Chairman for approval.  Remember, you cannot begin actual work on the project until the District Eagle Chairman or the District Advancement Chair approves your project.  A lot of planning should be done before you get that far.

Get a current copy of the Eagle Scout Leadership Service Project Workbook (a WORD version is available so you do all of your writing on the computer; see www.scouting.org), from the council office or from one of the troop leaders to use in preparing your plan.  This is the official booklet that is submitted to the district for approval.  Read everything in it before beginning to write-up your plan.  (The Troop 74 Eagle Scout Coordinator will provide a copy, paper or electronic.)

The project plan may be typed on a typewriter or computer, or may be hand written, but it must be very neat and written using proper grammar.  The plan should tell someone else everything they would need to know to carryout your project without you.  You should include the following information as shown in the workbook:

## Project Description

Briefly (approximately 1/2 to one page) describe the project.  This should not include any details - those will come later.  Address this section as though you were telling a friend what you were going to do.

### Who Will Benefit and How Will They Benefit

Name the group or organization that will benefit from your project and how your project will benefit them.  Remember, the project cannot benefit the Boy Scouts (except in the most indirect way).  Do not describe the project again, just focus on the benefit of the project.

## Planning Details

This is the heart of the project plan and the part that will require the most work.  The plan should include all details needed by someone else to carryout the project as though you were not there.  The plan will include the sections discussed below, if appropriate.  All sections are not applicable to all projects, so may be omitted if not needed.  Because there is limited space in the workbook, you may attach extra pages with the details.  You may prefer to write or type the plan on separate pages and then cut and paste them into the proper section of the workbook, or reference additional pages, after your adviser has helped you get it into the final form.  Alternatively, use the WORD version of the project workbook to prepare your write-up.

### Present Condition

Describe the current condition or situation that you are going to change.  Do not repeat the benefit of the project, but focus on creating a word picture of the current status.  This is a good place to include pictures (either photographs or drawings) of the project area.  Remember, the District Advancement Chair, Tom Roberts or District Eagle Board Chair, Jeff Stevenson, may not be familiar with your church, school, or park so they may not understand why your project is important unless you show and tell them.

### Plans/Drawings/Designs

If your project is to build something, you will need detail plans or drawings.  These are like blue prints and should show all dimensions, paint schemes, floor plans, layouts, or other detail that can be drawn.  Plans or drawings are usually done on graph paper that has guidelines, but blank paper is acceptable as long are you are neat.  Photographs may also be of value here for some projects.  If you have created a design (e.g. emblem, logo, etc.) include it in this section.  You may also use AutoCAD or PowerPoint to prepare your drawings or design.

### Materials

Materials are those items that become part of the finished product.  Examples are lumber, paint, nails, concrete, etc.  This is truly a shopping list, so include material specifications (exact size, quality, brand, finish, etc.), number of each item, and cost.  Don't just list "lumber"; you need to describe exactly what pieces of lumber.  If items are donated, indicate that in your materials list.  This section is best presented in the form of a separate list or table attached to extra pages in the workbook.

### Tools

Tools are those items used in making the work easier, or even make it possible to do at all.  Tools are not used up and should be saved and used again and again.  Examples of tools are hammers, shovels, tractors, or saws.  Provide a list of all tools required to work on the project.  Don't take for granted that required equipment will just appear when you need it.  Be very specific (e.g., number of hammers, type of shovels, type of paint brushes, etc.).  Tell how those tools will be obtained.  If you must purchase tools, include them in the financial plan (budget).  You should be able to borrow most tools from the people who are working on the project or from others.  Try not to spend much money on tools because they are expensive and not part of the finished product.  If you must buy tools, discuss what is going to be done with them after your project is complete.  Are you going to keep them, give them to the troop or other organization, or maybe to the organization who is funding the project?

### Supplies

Supplies are those expendable items that do not become part of the finished product, but are used to complete it.  Examples of supplies are sandpaper, trash bags, posters, gasoline, pens, markers, paper, paint rollers, drop cloths, etc.  Provide a list of all supplies you will need and where you will get them.  Because supplies cannot normally be reused, you need to either buy them or have them donated.  You cannot borrow something that you cannot return.  You may choose to combine the materials and supplies into one list; but label it as such.

### Schedule (Plan of Work)

A good schedule is a necessity for any successful plan.  It shows when everything is done and in what order each step must occur.  You must make your best estimate of how long tasks will take and in what order they will be done.  Your schedule may be in the form of a chart, a calendar with tasks entered on the appropriate days, or just a list of tasks and the date when they will be done.  Include project planning and approval on your schedule.  No project follows the planned schedule exactly, but is helps make things happen logically.  When you complete your project and do the final write-up, you will discuss how well the project followed the planned schedule and why you think you deviated from it.

### Step-by-Step Instructions

In addition to the schedule that shows the dates when you think tasks will be worked, you will also need detailed instructions.  These instructions should read like a recipe in a cookbook.  These tell the workers exactly what to do.  Include a list of every task you can think of, what order they will be done, who will do them.  Include the clean up of the work site in your plan.

### Financial Plan (Budget)

Every project will cost something and you need to itemize those costs.  Provide a list of all materials, tools, supplies, etc. with a cost of each.  This information may be part of your list of materials and supplies.  Indicate if items are borrowed or donated.  Remember to include fees (e.g., city dump fees) in your cost estimate.  Once you have determined how much the project is going to cost, you must find the money to pay for it.  You may consider several sources for funding, including the organization for which you are doing the project, donations from others, or any other legitimate source.  You may even need to conduct fund-raising activities to finance the supplies and materials needed for your project.  A scout or his parents should not pay for the entire project.  The scout may pay for some items, but these costs should not be a significant part of the overall cost. Obtaining the funds to do the project is your responsibility.  Don't assume that someone will cover costs until you have asked them and have it in writing.

A major part in any project, whether for Scouts, church, community, or a business, is funding.  If you cannot come up with all the money you need, look at reducing the cost to get within your budget.  You may even find that the project is too expensive and you will have to choose another one.

### Written /Printed Information

If you are going to use handouts, posters, letters, or other written materials as part of your project, include a copy of those in the plan.  These should be included as attachments to the workbook.

### Helpers/Workers

Discuss who will be doing the work.  You do not need to tell names, just the number of people, what organization they are part of, and what special skills will be required.  However, if you can make a list of potential helpers (with their phone numbers) it will help you get volunteers later.  For example, are you going to need a carpenter?  Describe how you are going to organize the workers to get the work done efficiently.  Will they be divided into teams, and if so, who will lead the teams?  What tasks will each team be doing?  How will you use adult leaders?  Discuss how you will ensure the safety of the workers.

Remember, you do not have to DO any of the physical work yourself; you are responsible for LEADING others in carrying out the project and ensuring that everything is done the way you want it (i.e., show leadership).

### Adult Supervision

Boy Scout policy requires at least two adult leaders be present at all times during any Scouting activity.  At least one of them must be Youth Protection trained.  It is your responsibility to ensure that this policy is followed.  Don't assume that the right people will just be there -- arrange, in advance, for them to be there.  You should state how you will ensure this in your plan.

### Work Site

Where will the work be done?  If you are going to build something, are you going to build it at the location where it will be used or somewhere else and then moved?  Remember, you must get permission to use any work site from the responsible person/owner.  If the location where you are going to work requires special facilities or tools, state so.  Think about how the weather will affect your work site.  Plan for alternate work dates.

### Transportation

Moving people, materials, supplies, tools to/from a work site will most likely be required.  Discuss what needs to be moved, what vehicles you will need, where you will get those vehicles, and who will drive.  The BSA policy places limitations on drivers under 21 years old; ensure you are aware of these limits and work within them.  Remember that all passengers must be seated with a seat belt on whenever a vehicle is in motion.  All of this is your responsibility.

### Safety

Think about the tools, site construction, electrical connections, and safety equipment that are needed.  Be prepared to supply gloves, goggles, or other safety items to your helpers.  If you are painting or creating dust in an interior space, be sure to provide adequate ventilation, including fans or other equipment.  Be sure that your plan has a written paragraph describing how you will assure safety at the worksite.  Have a first aid kit on site as needed.

# Step 3:  Initial Project Approval

There are several approvals required for your project along the way.  The first is the verbal approval from your Eagle Scout Coordinator (or Scoutmaster) that your idea will qualify as a valid project.  You need this before spending much time writing up the detail plan.  After your Eagle Scout Coordinator has helped you get the written plan in order and ready to submit, you will then need several signatures in the Eagle Scout Leadership Service Project Workbook.  A responsible representative from the organization you are doing the project for is the first signature required.  It is also a good idea to get a letter from the organization if possible.  Next, your Scoutmaster or Eagle Scout Coordinator signs, followed by the Troop Committee Chairman.  The project is now ready to turn in to the District Eagle Chair, Dr. Jeff Stevenson.

Contact Larry Parker:

Eagle Board Chairman

Address: 3116 Chic Circle, Manhattan, KS 66503

785-537-2413

lparker@kansasstatebank.com

You (the scout) will need to arrange to meet with him and discuss your proposal.  The meeting will take about 20 minutes.

Remember, it is very important that you DO NOT complete any part of your project, except planning, until the District Eagle Chairman has approved the project.  Once you have an approved plan, you can begin your project!  Once the project is begun, only minor changes should be made.  If you are having difficulty completing the project as approved, see your adviser or Scoutmaster.

# Step 4:  Completing the Project

Now that the hard part is over, you can begin the fun part - completing the project!  If you have prepared a good plan (which you will have), all you have to do is follow the plan and make the project happen.  Do what you said you were going to do.

It is important that you keep very good notes about everything that is done, including telephone calls.  Keep lists of all work done, who did the work, and other information as you go along.  Take photos of each stage of the work.  These will be included in the final report and will be a nice souvenir for your helpers and the time they spent.  For your final report, you need to discuss how well the plan worked and all areas where you were not able to follow the plan. So keep good track of this milestone in your life.  Keep track of all materials, supplies, tools, used, etc., paying particular attention to any differences from your original plan.  Save all receipts.

# Step 5:  Final Write-up

After the actual work on the project is completed, you are ready for the last phase of your project - the final report.  This is the section where you describe what actually happened as you carried out the plan.  This information is entered in the last section of the Eagle Scout Leadership Service Project Workbook, following the Initial Planning section that was approved by the District.

As with any project, it is important to review what was done and see what lessons were learned as well as providing a historic record.  In this case, you also need to write a final report because your project is not complete without it!  You should use the project plan as guide for preparing the final report.  In the “Carrying Out the Plan” workbook section, briefly describe what was done and how you deviated from the plan.  Go through each section of the plan and write a summary of the results versus the plan.  For example, discuss if you had all of the materials you needed or if you had a lot left over.  Summarize the actual costs, tools used (and tools needed that you did not have), or anything else of interest.

Provide a record of all the time worked by your volunteers.  This can be done in a list or table, showing names, dates, hours worked, tasks performed by each volunteer.  Discuss how you were able to lead the volunteers.  Leadership is the key ingredient to the Eagle project.  All methods you used and comments written in the report must emphasize that you were in charge and used appropriate leadership methods.  This can be greatly enhanced if you keep a log or a journal of all changes in plans, methods and/or decisions, no matter how small; and how you solved problems that occurred.  Did you have any problem with getting them to come to work or to stay focused on the assigned tasks?  Leading people is a challenging task and you most likely will have learned something about how to improve your leadership skills.  The final reviewers want to read about what you learned.

Plan to take many photos during each phase of the project.  Include a section in your report for representative photographs.  A photo of you presenting the finished product to the organization for whom you did the work would help show off the value of the project.  Make sure that all the photographs you use are labeled.

You will most likely require some advice from your project adviser before you are ready to turn the project in for final signatures.  Consult with him or her often as you are completing the report.  Once you and your adviser are happy with the result, it is time to get the final approval signatures.

# Step 6:  Final Project Approvals

Only a couple of signatures are required on your final report, the most important of which is yours.  If you are proud of your effort and pleased with the write-up, then sign it on the last page.  The only other signature is that of your Scoutmaster.  Although these are the only signatures required, the project's final approval will come during your Eagle Board of Review.

## Reference:  Recommendations

You will submit the project (plan and final report) along with your completed Eagle Scout application to the Coronado Area Council Service center through your Scoutmaster.  Along with your Eagle Scout Rank Application, you will need to request 5 or 6 references from individuals who know you personally and would provide a recommendation on your behalf.  Forms for the recommendation can be obtained from your scoutmaster or your troop Eagle Scout Coordinator.  Provide a return envelope addressed to your scoutmaster to the person providing the recommendation.

The recommendations should be UNOPENED and submitted by your scoutmaster or unit advancement chairman to the Council Office with your Eagle Application and final report.  Your Eagle Scout Leadership Service Project Workbook is kept until your Board of Review, and then returned to you.  Remember to always make a backup copy of your project workbook and the entire Eagle Scout application in case material is lost during the review and approval process.

Adapted from a document that was written in 1997 by Mr. Randall C. Smith, 6401 Tranquility Ct.,

Arlington, Texas 76016.  Subsequent changes were made by Bill Schapaugh, Manhattan, KS; Tom Roberts, Manhattan, KS; and Dr. Jeff Stevenson, Manhattan, KS.